## Sheet1
Stage | Activity | Dependencies | Delivery Due | Complete
Plan | 1a. Identify Project Scope |  | 3.23.25 | Yes
| 1b. Prepare Project Plan |  | 3.24.25 | Yes
| 1c. Select Algorithms | 1a | 3.25.25 | Yes
| 1d. Submit for approval |  | 3.30.25 | Yes
Execute | 2a. Define different data sets for exploration |  | 4.6.25 | Pending
| 2b. Design and implement algorithms | 1d, 2a | 4.10.25 | Pending
| 2c. Document process and collect data |  | 4.13.25 | Pending
Iterate | 3a. Analyze output for time and space complexity | 2c | 4.19.25 | Pending
| 3b. Compare algorithmic performance | 3a | 4.20.25 | Pending
| 3c. Implement any necessary updates | 3b | 4.23.25 | Pending
| 3d. Re-run data with updates | 3c | 4.24.25 | Pending
Report | 4a. Review and refine project documentation | 3d | 5.7.25 | Pending
| 4b. Create and Deliver Final Presentation |  | 5.11.25 | Pending